## Unloading- steel bar
Risk Assessment/Management Form
Ref:
Section / Dept: civil |  |  |  | Activity: RISK ASSESSMENT-UNLOADING OF REINFORCEMENT STEEL BY HYDRA
Sl.No. | Basic Job Steps | Potential Hazard | Consequence | Current Control Measures | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Unloading of reinforcement steel by hydra | Unauthorized Driving | Fatality/Machinery Damage | Only authorised person allow for driving | 1 | 0 | 0 | 1 | 2 | 2
Deployment only skill labours
Always switch off the engine before leaving from driver cabin
|  | Failure of operating systems | Fatality/Machinery Damage | Inspection required as per check list on daily basis before starting the operation
Weekly maintenance required and record should be kept in a registered
|  | Failure of slings /Fixing devices | Get injury/Fatality | Use of proper tested lifting equipments/devices
Deployment only skill workmen
Safety talk required on daily before starting the work
|  | Bursting of hydraulic hose | Get injury | For checking of hose pipe periodical inspection required
All the hose pipe must be purchased as per IS Std.and correct specification
No Person shall allow under the hanging load of hydra
2 | Unloading of the reinforcement steel (Manualy) | Personal Injury/Slip of materials | Get Injury | Only skilled &experienced work men deployed in the job with safety shoe ,hand gloves ,safety helmet and shoulder pad while unloading of reinforcement steel | 1 | 0 | 0 | 1 | 2 | 2
| Prepared By |  |  | Approved By | [5 empty] | Reviwed By