## Back Filling
Risk Assessment/Management Form
Ref:
Section / Dept: civil ,Contractor: |  |  |  | Activity: Risk Assessment for Backfilling | Location:
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Vehicle Inspection | Mechanical Failure | Get Injury | Vehicles to be used for backfilling(Dumper/Tractor-Trolley/JCB)to be checked for proper condition of brake atleast once a day before start of activity | 1 | 0 | 1 | 1 | 2 | 2
2 | Loading of materials | Hit to a person/Equipment/Vehicle | Get Injury/Fatality | No person should stand under the swing area and on the dallah of the dumper | 1 | 0 | 1 | 0 | 2 | 2
|  | Rolled down of vehicle |  | Metallic stopper available with vehicles to be used to protect accidental rolling
Physical barriers like slippers to be used to prevent vehicles rolling down a slope
3 | Transportation of material | Hit to a person/Vehicle | Get Injury/Fatality | The vehicle should follow the traffic rule | 2 | 0 | 1 | 1 | 2 | 4
The vehicle must be in good condition
License holder operator can operate the vehicle
No undulation of road
No overtaking at site
All overhead are to be isolated/ removed
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
4 | Backfilling/ Unloading of material at site | Toppled/Tilting of vehicle | Get Injury/Fatality | Safe access shall be provided for unloading the sand/soil | 2 | 0 | 2 | 1 | 2 | 4
|  | Collapse of soil/pits |  | Use stopper at the time of unloading
|  | Hit to a person /vehicle |  | No motor boy will stay behind the vehicle and maintained safe distance from the vehicle
5 | Levelling by machine | Hit to a person and Structure damage | Get Injury/Fatality | Guide by a supervisor to avoid such risk | 1 | 0 | 1 | 1 | 2 | 2
No person shall work in levelling area
Checking of live lighting cable
All the work must be done under strict supervision
6 | Operating of Earth compactor | Electrical injury | Get Injury/Fatality | Only authorised experience person shall be deployed in the job with safety shoe , helmet, jacket, goggles and rubber hand gloves | 2 | 0 | 0 | 1 | 2 | 4
Proper earthing to be provided and it should be checked by authorised electrician at regular intervals
|  |  |  | Approved By | [6 empty] | Reviewed By
|  |  |  | MR.S.K.GOSWAMI | [6 empty] | SANJAY ACHARYA
|  | Dust exposure | Effects on lungs during long time exposure | Use of good quality nose mask | 1 | 0 | 0 | 1 | 2 | 2
|  | Emission of noise | Hearing loss | Use of ear plug | 1 | 0 | 0 | 0 | 2 | 2
| Prepared By |  |  | Approved By | [6 empty] | Reviewed By
| Contractor |  |  | Contractor