## Concreting
Risk Assessment/Management Form
Ref:
Section / Dept: civil,Contractor: |  |  |  | Activity: Risk Assessment for Concreting | Location:
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Concreting Manualy | Fall of man / materials | Get Injury | Proper illumination arranged at the working area in night. | 1 | 0 | 0 | 0 | 2 | 2
Passage to be provided for the movement of the person
Edge protected by railing / scaffolding pipe and use of double rope safety belt with anchoring facilities
Before concreting work all area to be barricated at lower level
2 | Concreting by bucket | Fall of material | Get Injury/Fatality | When the bucket being lifted is out of sight of the crane operator,a signal man shall be posted in clear view of the receiving area and the crane operetor and signalman must be wearing of floroscent jacket | 1 | 0 | 0 | 0 | 2 | 2
It should be preferably equipped with safety latch
Closing and locking of the exit door of the bucket shall always be checked by the supervisor of loading concrete in the bucket for avoiding accidental opening of the exit door and consequence falling of concrete
Area must be barricated by scaffolding pipe
2 | Working at Height in night | Improper Visibility | Injury/Fatality | Proper illumination with WAH petrmit | 1 | 0 | 0 | 0 | 4 | 4
|  | Fall of person /materials during Power Failure | Injury/Fatality | Emergency Light shall be availabe at site.People will stop the work and communicated not to be panic in case of pwer failure. All will remain in the same place till the alternative arrangement of light.Emergency Torchlight to be facilitated for working crew -Min-03 no.s.Definite supervisor for each area and additonal incharge overall
|  | work stopped more than half an hour. | Injury/Fatality | Any work stopped due any reason in the late niight more than 1/2 hour. Idle people should not rest in the work area. They should come back to site office to relax and properly advise during tool box talk every shift
| Prepared By |  |  | Approved By | [6 empty] | Reviewed By