## Tunnel
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment for Finishing work | Location/Area:-
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Brick & Plastering on wall | Slip of materials/Tools | Get Injury | Platform to be made as per standard and it should be certified | 2 | 0 | 0 | 0 | 2 | 4
Use of Double rope full body harness and it shoud be anchored above the head height at different two anchoring points
Use of rubber hand gloves for avoiding of skin hazards
Drop Zone to be provided
Toe guard to be provided for preventing from materials
Loose materials shall not be allowed to remain on the gangways
|  | Working at height | Get Injury/Fatality | Take WAH permit before starting the activity | 2 | 0 | 0 | 1 | 2 | 4
Enlist the name of workmenat daily attachment sheet before starting the activity
Finishing activity at reject silo wall to be carried on sitting inside the jhola which is to be hanged with reject silo wall while require the changing the position of work place,people shall go carefully from jhola to silo shell with anchoring safety harness.
| Prepaired By |  |  | Approved By | Reviwed by
| Contractor |  |  | Contractor
| Date |  |  | Date | Date
#REF!
#REF!