## Cutting
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment-Cutting work | Location/Area -
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measures | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Transportation of Gas cylinder | Fall from vehicle/Cylinder Trolley during transportation | Get Injury | To Provide fire Extinguisher before starting the activity | 1 | 0 | 0 | 0 | 2 | 2
All gas cylinders shall be kept upright and cylinder shall not strike each other at the time of transport,proper loading of cylinders shall be ensured
Cylinder shall never be rolled on ground,it has to be carried out by cylinder trolly only
2 | Unloading of cylinder | Fall from vehicle and Explosion | Get Injury/Fatality | Gas cylinder shall be unloaded with sufficient manpower to prevent any kind of fall or damage due to unloading | 2 | 0 | 0 | 2 | 2 | 4
Gas cylinder shall be kept away always from lubricants and must have the valve cap protection to prevent any kind of damage to cylinder valve
3 | Fixing or connecting gas hose | Leackage of hose pipe | Get Injury due to fire | All hose pipes shall be inspected for any kind of damage or leakage prior to start the days work. | 1 | 0 | 0 | 0 | 2 | 2
Take hot work permit before starting the activity
4 | Working at Height | Fall from Height | Get Injury/Fatality | Providing full body safety harness to the workers working at height | 2 | 0 | 0 | 2 | 3 | 6 | Daily Tool Box talk | 2 | 0 | 0 | 2 | 2 | 4
Providing proper anchoring point to anchor the full body safety harness.Platform &staging to be made as per standard.
| Prepared By |  |  | Approved By | [6 empty] | Reviwed By
| Contractor |  |  | Contractor
| Date |  |  | Date | [6 empty] | Date