## Dismandling of cement slab
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment For Dismantling of cement silo | Location:-
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Climbing up on the top of the Cement Silo for anchoring the sling | Fall of man due to slip | Get Injury/Fatality | Deployment only experienced workmen | 1 | 0 | 0 | 1 | 2 | 2
To fill up the Wah permit & daily attachment sheet before starting the activity
Use double rope full body harness while ascending or descending
Daily checked all the tools before starting the activity
|  | Slip of tools/Materials |  | All the portable tools must be tied with rope while working for preventing the accidental fall
|  | Working at height | Get Injury/Fatality | Only authorised persons are allowed for working at height
Use double rope full body harness and it must be anchored above the head height.
Use of safety shoe,Helmet with chin strip & Hand gloves
2 | Cutting of supporting structure & bolt at ground level | Fall from vehicle/Cylinder Trolley during transportation | Get Injury | To Provide fire Extinguisher before starting the activity | 2 | 0 | 0 | 2 | 2 | 4
All gas cylinders shall be kept upright and cylinder shall not strike each other at the time of transport,proper loading of cylinders shall be ensured
Cylinder shall never be rolled on ground,it has to be carried out by cylinder trolly only
|  | Fall from vehicle and Explosion |  | Gas cylinder shall be unloaded with sufficient manpower to prevent any kind of fall or damage due to unloading
Gas cylinder shall be kept away always from lubricants and must have the valve cap protection to prevent any kind of damage to cylinder valve
|  | Leackage of hose pipe |  | All hose pipes shall be inspected for any kind of damage or leakage prior to start the days work.
Take hot work permit before starting the activity
3 | Lowering of silo by crawler crane | Failure of slings | Get Injury/Fatality | Load must be lifted as per sequence of load chart | 2 | 0 | 0 | 1 | 2 | 4
Capacity of Crane must be in accordance with the weight of the load
All slings and D-shackles used for erection shall have third party inspection certificate & they must be checked visually before starting the job.
|  | Fall of loose materials | Get Injury | All the loose materials should be lowered by gunny bag with rope pully system.
The swing area should be barricaded and nobody to be allowed under the suspended load
| Prepared By |  |  | Approved By | [6 empty] | Reviewd By
| Contractor |  |  | Contractor
| Date |  |  | Date | [6 empty] | Date