## Dis.man-Concrete pump tower
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment -Dismantling of staging | Location-
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Climbing up on the top of the scaffolding | Fall of man due to slip | Get Injury/Fatality | Deployment only experienced workmen | 1 | 0 | 0 | 0 | 2 | 2
Only authorised persons are allowed for working at height
To fill up the Wah permit & daily attachment sheet before starting the activity
|  |  |  | Use double rope full body harness while ascending or descending | 2 | 0 | 0 | 1 | 2 | 4
Daily checked all the tools before starting the activity
|  | Slip of tools/Materials |  | All the portable tools must be tied with rope while working for preventing the accidental fall
2 | Lowering of pipe,clamps planks etc.by using rope pulley | Slip/Fall of materials | Get Injury/Fatality | Area should be properly barricaded and nobody allow under the suspended load | 2 | 0 | 0 | 1 | 2 | 4
Deployment only experienced workmen
Pulley and rope must be checked before starting the activity on daily basis
Deployment only experienced workmen
Pulley and rope must be checked before starting the activity on daily basis
|  | Working at height | Get Injury/Fatality | Only authorised persons are allowed for working at height
Use double rope full body harness and it must be fixed above the head height
Use of safety shoe,Helmet with chin strip & Hand gloves
3 | Shifting of the dismantled materials to a designated place | Slip of man/Fall of materials | Get Injury/Fatality | Movement of path is to be free from any obstruction | 1 | 0 | 0 | 1 | 2 | 2
All the materials should be stored in a proper place and kept it in orderly manner
Tool box talk required on daily basis before starting the activity
4 | Working at height | Slip of man/Fall of materials | Get Injury/Fatality | Access to be provided for acsending and descending through the ladder (min. gap 500mm with the stagging) , Lynyards of full body safety harness are to be anchored in two separate anchoring points. , In case of bad weather i.e rain work must be stopped. | 2 | 0 | 0 | 2 | 3 | 6 | Daily tool box talk | 2 | 0 | 0 | 2 | 2 | 4
| Prepaired by: |  |  | Approved by: | Reviwed by:
| Contractor |  |  | Contractor
| Date |  |  | Date | Date
| Prepaired by |  |  | Approved By | [6 empty] | Reviewed By