## Dismandlin of staging
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor:- |  |  |  | Activity: Risk Assessment-Dismantling of staging Work | Location:-
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measures | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Climbing up on the top of the scaffolding | Fall of man due to slip | Get Injury | Working plateorm to be made for every 2.1m with double railings,toeguard and scaffolding staging ladder as access whose rungs are not spaced greater than 500mm | 1 | 0 | 0 | 0 | 2 | 2
Use of Double rope full body safety harness and one point must be achored at all times while ascending or descending
2 | Arrangement of platform for Destaging | Fall of man/Materials | Get Injury/Fatality | Deployment only experienced workmen | 2 | 0 | 0 | 1 | 2 | 4
|  | Fall of materials | Get Injury | Lifting of planks are to be done by rope/binding wire
All the planks are to be tied up with coir rope
3 | Dismantling of staging | Fall of materials | Get Injury/Fatality | Deployment only experienced workmen | 2 | 0 | 0 | 0 | 3 | 6 | To established the drop zone at the ground level & give the Daily tool box Talk | 1 | 0 | 1 | 0 | 2 | 2
Use of Double rope safety harness and it must be fixed above the head height
Barricade the area below.
Use of safety shoes,Helmet with chin strip and hand gloves
4 | Lowering of pipe& clamps | Fall of materials/man | Fall of materials/man | All the materials shall be lowered down by rope | 2 | 0 | 0 | 1 | 2 | 4
All the loose materials shall be collected in a gunny bag
Use of Double rope safety harness and it must be fixed above the head height
5 | Shifting of the dismantled materials to a designated place | Slip of man/Fall of materials | Get Injury/Fatality | Movement of path is to be free from any obstruction | 2 | 0 | 0 | 1 | 2 | 4
Material means --Staging pipes & clamps.
Additional Risk Assesment
1 | Full body safety harness with double lynyard to be used and its hooks must be anchered at two different points.
2 | Skilled Supervisor to be deployed at the time of dismantling
3 | Sufficient illumination to be provided at night work
4 | Proper working platform with tightened planks to be provided for dismantling.
5 | Tool box talk before starting of the work
6 | No material shoul be thrown from top to bottom
| Prepaired by |  |  | Approved by | [6 empty] | Reviewed by
| contractor |  |  | contractor
| Date |  |  | Date | [6 empty] | Date