## Erc.column, stair case
Risk Assessment/Management Form
Ref:
Section / Dept: Preheater / civil |  |  |  | Activity: Risk Assessment-ERECTION OF COLUMN,STAIR CASE AND BRACING
Sl N. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Shifting of the materials by Hydra up to max. 2 MT | Fall of materials | Get Injury/ Fatality | Use guide rope during shifting of materials and always keep away from swing area.Daily tool box talk before starting of job by crew supervisor. | 1 | 0 | 0 | 1 | 2 | 2
|  | Failure of wire rope sling/D-shackle | Get Injury | All the wire rope sling & D-shackle must be visually checked . Tested sling must be colour coaded by a specific colour .aily tool box talk before starting of job by crew supervisor.
|  | Hooking of material | Get injury | Skilled workmen shall be engaged for hooking of material.Hook of hydra must be provided with hook latchaily tool box talk before starting of job by crew supervisor.
|  | Shifting of material | Get injury | People should maintain safe distance from the load while lifting and shifting.Guied rope to be fixed on both ends of the material.Communication with the hydra operatot will be one to one talk and signal will be issued by the signal man with blue helmet.
|  | Shifting of material |  | People should maitain safe distance from the load while lifting and shifting.Guide rope to be fixed on both ends of the material.Communication with the hydra operator will be one to one talk and signal will be issued by the signal man with blue helmet.
|  | Unhooking of material | Injury to person | People should not unhook the sling during tension. Only skilled person will remove the sling from the hook.
|  | Toppling of Hydra due to excess loading | Injury / Fatality | Marking of SWL at different lifting hooks of hydra. Only Trained & experienced operator will operate the hydra.Material above the safe working load mentioned at the lifting position shall not be lifted.
|  | Traffic Control | Man/Materials loss | Deploy one hydra helper with whistle wearing of floroscent jacket walking minimum 3m.away from hydra(left side) and 2persons are to be standing for the guidence of guide rope & Hydra speed can be resticted , Reverse horn sounds during reversal of hydra.
|  | Traffic Control | Man/Materials Loss | Deploy one hydra helper with whistle wearing of floroscent jacket walking minimum 3m.away from hydra(left side) and 2persons are to be standing for the guidence of guide rope&Hydra speed can be restricted.Reverse horn sounds during reversal of hydra.
2 | Stacking of materials | Tripping | Get Injury | All the materials shall be stacked at designated place | 1 | 0 | 0 | 0 | 2 | 2
|  | Unloading & Stacking | Get Injury | Height of stacked materials shall be maintained as per safety norms & users convenience
Stacking shall be done as per the shape,size & weight of the materials
3 | Lifting of materials | Slip of Tools | Get Injury | Lifting of materials up to 40m.to be done by Crawler Crane & Rest of height shall be done by Tower Crane | 2 | 0 | 0 | 1 | 2 | 4
All the tools should be tied up with rope while using
|  | Fall of materials | Get Injury | All the loose materials should be lifted by gunny bag with rope pully system/winch m/c
Area should be barricaded and nobody allow under the suspended load
4 | Erection of Col.fitted with bracing | Failure of slings | Get Injury/Fatality | Ascending and Descending of workmen shall be done through the Erected stair and the stair must be fitted with hand rails | 2 | 0 | 1 | 1 | 2 | 4
All slings and D-shackles used for erection shall have third party inspection certificate
Capacity of Hydra/Crane must be in accordance with the weight of the load
During erection the signal man must be wearing of reflective jacket
Load must be lifted as per sequence of load chart
After erection the structures will be anchor bolted/grouted
Erection team employed in erection must be skilled & identified
5 | Erection of supporting members | Fall from height | Get Injury/Fatality | All supporting members should be bolted/welded properly | 2 | 0 | 0 | 1 | 2 | 4
To arrange the working platform out side the preheater building for the erection of supporting members
While person working out side the preheater he must be wearing of double rope safety harness and it should be tied up with the fixed structure above the head height
6 | Working at height | Fall from height | Get Injury/Fatality | Take Wah permit before starting the activity | 3 | 0 | 0 | 2 | 2 | 6 | Co-ordinated Tool box talk daily | 2 | 0 | 0 | 0 | 2 | 4
Use double rope full body harness for ascending and descending
Always anchor the safety belt above the head height
Proper scaffold as work platform shall be made
The erection team employed in erection must be skilled & identified
7 | Welding | Electric shock | Get Injury /Respiratory problem | Only Trained & Experienced personnel shall be allowed for welding | 2 | 0 | 0 | 2 | 3 | 6 | Co-ordinated Tool box talk daily | 2 | 0 | 0 | 1 | 2 | 4
To take charging approval
Welding m/c.should be connected with separate earthing
To use welding appropriate PPE
|  | Eye Injury | Damage of both eyes | Looking at welders ARC should be avoided while working with in the vicinity of welding
Use welding screen of correct specification
Use of proper PPE
8 | Gas cutting activity | Leackage of hose pipe | Get Injury due to fire | All hose pipes shall be inspected for any kind of damage or leakage prior to start the days work. | 2 | 1 | 0 | 0 | 2 | 4
Take hot work permit before starting the activity
Proper hose clamp shall be provided at both cylinder side and torch side.
Binding wire shall never be used or allowed inplace of hose clamp
Colour code for separate hose pipe (Red for DA and blue for Oxygen) shall be maintained and never be mixed
|  | Fire due to use of improper lighting tools & torch | Get Injury | Only striking lighter shall be used to light the torch and torch shall be checked for any kind of damages prio to start the job
Flash Back arrester shall be provided to all the outlets of cylinders
Pressure guages (both for working pressure and cylinder pressure) shall be maintained
Cleaning of torch from dirt required on daily basis
9 | Natural Calamity | High wind Velocity | Injury/Fatality | To stop the work and reassess the condition | 1 | 0 | 0 | 0 | 4 | 4
Avoiding high tonnage erection(>5T) DURING NIGHT HOURS
Any work stopped due any reasonin the late night more than 1/2 hr.idle people should not restin the work area.They should come back to site office for relax
| Prepaired by: |  |  | Approved by: | [6 empty] | Reviewed by:
Proper supporting of chute required
Nobody allow top of the chute
No body allow under the chute
Deploy only experience workmen