## Lifting of materials on the top
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment for Lifting of materials on the top of Room by Tower crane | Location / Area :-
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Lifting of Bricks and Sand by Tower crane | Fall of materials | Get Injury/Fatality | Only authorised person allow for driving | 2 | 0 | 0 | 1 | 2 | 4
Only trained person allow for signaling and signal man should be worne Floroscent jacket
Nobody allow under the suspended load
|  | Failure of slings/Fixing Devices | Get Injury/Fatality | Use of proper tested lifting equipments/devices
Deployment only skill workmen
Communication system will be done through Walky-Talky between operator and other workmen
Materials lifting should be done as per sequence of load chart
Bricks to be lifted through the busket
2 | Unloading of materials | Fall of man at the edge of roof | Get Injury | All the materials should be unloaded at the centre of the roof | 1 | 0 | 0 | 1 | 2 | 2
1no.supervisor to be deployed at all times
To use of proper PPE during unloading the materials
To follow the existance system of WAH
| Prepared By |  |  | Approved By | [6 empty] | Reviewed By
| MR.S.ADHIKARY |  |  | MR.S.K.GOSWAMI | [6 empty] | SANJAY ACHARYA
| Prepared By |  |  | Approved By | [6 empty] | Reviwed By
Note on C14: abc: