## Passenger-Hoist lifting
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment -Passenger hoist lift | LOCATION:
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Making of passenger hoist foundation | Fall of excavated pit | Get Injury | Barricade the area by caution tape | 1 | 0 | 0 | 0 | 2 | 2
Foundation will be made as per construction drawing & certified by competent person from simplex site
2 | Shifting of materials by Hydra | Failure of slings/Fixing devices | Get Injury | Use only Tested slings/Fixing devices | 1 | 0 | 0 | 0 | 2 | 2
Before lifting it should ensured that lifted load must be equally balanced
Use guide rope on both sides
Deployment only skill workmen
Use of proper ppe
3 | Fixing of parts with the help of Tower crane | Unauthorised driving | Fatality/Machinery Damaged | Only authorised persons are allow for operating the Tower crane | 2 | 0 | 0 | 1 | 2 | 4
Only trained persons are allow for signaling & signal man must be worned floroscent jacket
Deployment only skill workmen
Use of proper ppe
To provide safemeans of access/Provided ladder in side of passenger lift
Materials lifting should be done as per load chart
There should be good communication system between Tower Crane operator & other workmen
To provide safemeans of access/Provided ladder in side of passenger lift
Materials lifting should be done as per load chart
There should be good communication system between Tower Crane operator & other workmen
4 | Drilling on holes&fixing anchor bolts | Not proper holes in preheater building | Man fatality/Machinery Damaged | Drilling done as per insutructed by Meka Ster compony | 1 | 0 | 0 | 1 | 2 | 2
5 | In case of cutt off power supply | Damage of cable line or Electric motor | Stop the lift in case of motion | Provided interlock system in passenger lift | 1 | 0 | 0 | 1 | 2 | 2
Have mechanical arragement for go down when power is cutt
6 | Providing Connection of Electric Supply to passenger Hoist | Electric shock | Get Injury/Fatality | Provide elctrical safety as per manual | 2 | 0 | 0 | 1 | 2 | 4
There should not be any high voltage line present within 5.2m.radius of the passenger hoist top
Inbuilt safemeans of access must be required for ascending and descending
| Prepaired by: |  |  | Approved by: | Reviwed by:
| Contractor |  |  | Contractor
| Date |  |  | Date | Date
| Prepaired by |  |  | Approved By | [6 empty] | Reviewed By