## Sand filling
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment-Sand Filling | Location/Area :
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measures | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Unloading of sand at site | Collapse of soil/pits,hit to aperson,collaps-e of soil. | Get Injury/Fatality | Use stopper at the time of unloading | 2 | 0 | 0 | 2 | 2 | 4
No motor boy will stay behind the vehicle and maintained safe distance from the vehicle
Safe access shall be provided for unloading the sand/soil
2 | Shifting of sand to the tunnel manually | Slip of iron pan from the hand, Slip of man | Get Injury | Strict supervision to be provided for the job | 1 | 0 | 0 | 0 | 2 | 2
|  |  |  | Persons shall be deployed in the job with safety shoe , helmet, jacket, goggles and rubber hand gloves | 1 | 0 | 0 | 0 | 2 | 2
3 | Working at height | Falling from height | Get Injury due to fall | Workers will provided with full body safety harness
Take height work permit before starting the activity
| Prepared By |  |  | Approved By | [6 empty] | Reviwed By
| Contractor |  |  | Contractor | [6 empty] | Contractor
| Date |  |  | Date | [6 empty] | Date