## Tunnel-slab work
Risk Assessment/Management Form
Ref:
Section / Dept: civil |  |  |  | Activity: Risk Assessment for Tunnel Work Slab
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Shifting of the materials (Manualy) | Personal Injury/Slip of materials | Get Injury | Only skilled &experienced work men deployed in the job with safety shoe ,hand gloves ,safety helmet and shoulder pad while shifting of materials | 1 | 0 | 0 | 1 | 2 | 2
2 | Shifting of the reinforcement materials by Hydra up to max. 2 MT | Fall of materials | Get Injury/ Fatality | Only skilled &experienced work men deployed in the job with safety shoe ,hand gloves ,safety helmet and tested tools &tackles. Use guide rope during shifting of materials and always keep away from swing area.Daily tool box talk before starting of job by crew supervisor. | 1 | 0 | 0 | 1 | 4 | 4
|  | Failure of wire rope sling/D-shackle | Get Injury | All the wire rope sling & D-shackle visually checked . Tested sling are colour coaded by a specific colour .Daily tool box talk before starting of job by crew supervisor.
|  | Hooking of material | Get injury | Skilled workmen shall be engaged for hooking of material.Hook of hydra must be provided with hook latchaily tool box talk before starting of job by crew supervisor.
|  | Shifting of material | Get injury | People should maintain safe distance from the load while lifting and shifting.Guied rope to be fixed on both ends of the material.Communication with the hydra operatot will be one to one talk and signal will be issued by the signal man with blue helmet.
|  | Unhooking of material | Injury to person | People should not unhook the sling during tension. Only skilled person will remove the sling from the hook.
|  | Toppling of Hydra due to excess loading | Injury / Fatality | Marking of SWL at different lifting hooks of hydra. Only Trained & experienced operator operate the hydra.Material above the safe working load mentioned at the lifting position shall not be lifted.
|  | Traffic Control | Man/Materials loss | One hydra helper will be deployed with whistle wearing of fluroscent jacket walking maintaining safe distance from hydra(left side) and 2persons are to be standing for the guidence of guide rope & Hydra speed resticted , Reverse horn during reversal of hydra.
3 | Reinforcement Laying and Binding | Slip/Fall of materials | Get Injury | Only skilled &experienced work men will be deployed in the job with safety shoe ,hand gloves ,safety helmet and proper tools &tackles. proper illumination arranged at the working area in night. .Positioning , supporting and fixing of reinforcement by binding wire. | 1 | 0 | 0 | 1 | 4 | 4
|  | Collapsing of vertical 'H' Frame | Get Injury/Fatality | All the fitted 'H' Frame properly fixed by Clamping and extended by jack.Distance between Two 'H' Frame 800mm(Spacing) & Horizontal spacing 600mm.
4 | Accesss for Raft | slip of man | Injury | Ramps with hand railing provided for ascending and descending of persons to the raft.Planks provided in the approach area over the raft.The planks are to be tied with binding wire.
5 | Shuttering | Slip of man/ materials | Get Injury | Only skilled &experienced work men deployed in the job with safety shoe ,hand gloves and safety helmet..Staging provided for shuttering activity with tied planks on the platform to stand. Full body double rope safety harness provided for anchoring above the head height with shorter length . | 2 | 0 | 0 | 1 | 2 | 4
6 | Concreting by pump | Cleaning of pipe line | Get Injury | After assembly it should be checked thoroughly.Scaffolding tower to be made for concrete pump pipe line. | 1 | 0 | 0 | 0 | 2 | 2
|  | Nip Hazards | Get Injury/Fatality | All the revolving parts should be well guarded
|  | Emission of Noise | Permanent/Temporary hearing loss | Use Ear plug/Ear muff
7 | Operation of Vibrator | Electrical shock | Get Injury/Fatality | Charging approval must be taken from competent authority before starting the activity.Double earthing of eqpt shall be ensured before use.Electrical connection should be through proper ELCB.Daily tool box talk before starting of job.Use of Non-Conductive sole safety shoe,safety helmet . | 1 | 0 | 0 | 0 | 4 | 4
|  | Flying of the Concrete slurry | Eye Injury | Deployed only experienced workmen with safety goggles
|  | Slip of the m/c.while shifting | Get Injury | Use of proper hand gloves,safety shoesand helmets with carefully .
| Working at Height | Fall of materials / Fall of person | Injury/Fatality | WAH permit shall be followed strictly for people working at height more than 1.8 meter.
8 | Working at Height in night | Improper Visibility | Injury/Fatality | proper illumination with WAH petrmit | 1 | 0 | 0 | 0 | 4 | 4
|  | Fall of person /materials during Power Failure | Injury/Fatality | Emergency Light shall be availabe at site.People will stop the work and communicated not to be panic in case of pwer failure. All will remain in the same place till the alternative arrangement of light.Emergency Torchlight to be facilitated for working crew -Min-03 no.s.Definite supervisor for each area and additonal incharge overall
|  | work stopped more than half an hour. | Injury/Fatality | Any work stopped due any reason in the late niight more than 1/2 hour. Idle people should not rest in the work area. They should come back to site office to relax and properly advise during tool box talk every shift
| Prepared By | [9 empty] | Reviewed By
Date