## Winch machine
Risk Assessment/Management Form
Ref:
Section / Dept: civil Contractor :- |  |  |  | Activity: Risk Assessment -Operation of Winch Machine | LOCATION:
Sl No. | Basic Job Steps | Potential Hazard | Consequence | Current control measure | Risk rating |  |  |  | Probability | Initial Risk | Additional control measure | Risk rating |  |  |  | Probability | Residual risk
[5 empty] | P | E | A | R |  |  |  | P | E | A | R
1 | Shifting of Winch M/C at work Location | Striking with the man/materials | Get Injury | Machine to be shifted by Hydra | 1 | 0 | 0 | 0 | 2 | 2
|  | Failure of wire rope sling & D-shackle | Get Injury | Uses of tested wire rope sling & D-shackle and all the tested lifting equipments should be colour coaded | 1 | 0 | 0 | 0 | 2 | 2
It should be ensured the load which is lifted by hydra must be equally balanced before shifting same
During shifting of m/c.guide rope should be provided in both sides.
Nobody allow within 2mts.distance of the hanging load
Pathway should be even and free from any other obstruction
2 | Fixing of m/c. | Tripping hazards | Get Injury | Surface should be compact soil where m/c.to be provided and it should be supported with the fixed structure by welding | 2 | 0 | 0 | 0 | 2 | 4
Deployment only skilled workmen
Use of proper PPE
3 | Operation of winch m/c for lifting of materials | Powe failure at the time of lowering/hoisting the load | Get Injury | To check the periodic break arrangements | 1 | 0 | 0 | 0 | 2 | 2
To check the hold break locking arrangements
Tool-Box talk to be conducted on daily before starting the activity
Area barrication to be provided
Only authorised persons are to be allowed inside the barrication
|  | Nip hazards | Get Injury/Fatality | Rotating/moving parts of motor and winch Flywheel to be properly guarded | 2 | 0 | 0 | 1 | 2 | 4
|  | Electrical shock | Get Injury/Fatality | Electrical operations to be carried out by authorized electricians | 2 | 0 | 0 | 2 | 2 | 4
Use of 30ml Amps ELCB and to provide double earthin with the winch connection
Take charging approval before operation
Only authorised person shall operate the m/c.
Double insulated cables to be used with all the electrical connections
|  | Failure of pulley | Get Injury/Fatality | Proper lubrication to be provided of the winch ropes,pulley & gears etc. | 2 | 0 | 0 | 1 | 2 | 4
Periodical checking of pulley pin should be required
| Prepaired by: |  |  | Approved by: | [7 empty] | Reviwed by:
| Contractor |  |  | Contractor
| Date |  |  | Date | [7 empty] | Date